The monthly distribution below follows the project phases in the proposal:

- M1–M3: Data collection, integration and project initiation

- M4–M6: Climate trend and climate-health analysis

- M7–M10: AI/ML development and validation

- M11–M13: GIS, vulnerability mapping and HHRI

- M14–M17: Dashboard, mobile alert system, stakeholder validation

- M18: Final deployment, dissemination and reporting

Monthly Budget Requirement

| Month | Major activity emphasis | Monthly requirement (₹) | Cumulative (₹) |
| --- | --- | --- | --- |
| 1 | Project initiation & data collection | 1,95,000 | 1,95,000 |
| 2 | Data collection & database creation | 1,95,000 | 3,90,000 |
| 3 | Data integration & stakeholder consultation | 1,95,000 | 5,85,000 |
| 4 | Climate trend & health analysis | 2,05,000 | 7,90,000 |
| 5 | Climate-health linkage analysis | 2,05,000 | 9,95,000 |
| 6 | Threshold/risk analysis | 2,05,000 | 12,00,000 |
| 7 | AI/ML model development | 2,30,000 | 14,30,000 |
| 8 | RF/XGBoost/LSTM development | 2,30,000 | 16,60,000 |
| 9 | Model testing & validation | 2,30,000 | 18,90,000 |
| 10 | AI model refinement | 2,30,000 | 21,20,000 |
| 11 | GIS vulnerability analysis | 2,38,000 | 23,58,000 |
| 12 | HHRI development | 2,38,000 | 25,97,000 |
| 13 | District/city vulnerability mapping | 2,38,000 | 28,35,000 |
| 14 | Dashboard development | 2,62,000 | 30,97,000 |
| 15 | Dashboard + mobile alert development | 2,62,000 | 33,59,000 |
| 16 | Integration & user testing | 2,62,000 | 36,21,000 |
| 17 | Stakeholder validation & deployment | 2,62,000 | 38,83,000 |
| 18 | Final reporting, dissemination & scale-up | 3,77,000 | 42,60,000 |
| Total |  |  | 42,60,000 |

Quarterly Budget Requirement

| Quarter | Months | Major activities | Requirement (₹ lakh) | % of total |
| --- | --- | --- | --- | --- |
| Q1 | M1–M3 | Initiation, data collection & integration | 5.85 | 13.73% |
| Q2 | M4–M6 | Climate trend & health analysis | 6.15 | 14.44% |
| Q3 | M7–M9 | AI/ML development & initial validation | 6.90 | 16.20% |
| Q4 | M10–M12 | AI validation, GIS & HHRI development | 7.07 | 16.59% |
| Q5 | M13–M15 | Vulnerability mapping & dashboard development | 7.62 | 17.89% |
| Q6 | M16–M18 | System validation, deployment & dissemination | 9.01 | 21.15% |
| Total | 18 months |  | ₹42.60 lakh | 100% |

# Budget in the Ratio 35: 35: 30

### Total = ₹42,60,000

| ### Instalment | ### Ratio | ### Calculation | ### Amount |
| --- | --- | --- | --- |
| ### 1st Instalment | ### 35% | ### ₹42,60,000 × 35% | ### ₹14,91,000 |
| ### 2nd Instalment | ### 35% | ### ₹42,60,000 × 35% | ### ₹14,91,000 |
| ### 3rd Instalment | ### 30% | ### ₹42,60,000 × 30% | ### ₹12,78,000 |
| ### Total | ### 100% |  | ### ₹42,60,000 |

### Recommended mapping to project phases

| ### Instalment | ### Period | ### Amount | ### Suggested utilisation |
| --- | --- | --- | --- |
| ### I | ### Months 1–6 | ### ₹14.91 lakh | ### Personnel, initial data acquisition, database creation, cloud infrastructure, initial climate-health analysis |
| ### II | ### Months 7–12 | ### ₹14.91 lakh | ### AI/ML model development, validation, GIS analysis, HHRI development, cloud computing |
| ### III | ### Months 13–18 | ### ₹12.78 lakh | ### Vulnerability mapping, dashboard, mobile alerts, stakeholder validation, dissemination and final reporting |
| ### Total | ### 18 months | ### ₹42.60 lakh |  |

This is particularly suitable if the 35:35:30 ratio refers to fund-release/instalment requirements, rather than an exact representation of monthly expenditure.

Data Collection Agencies for Secondary Data Collection

## 1. India Meteorological Department — Meteorological Centre, Ahmedabad

Primary role: Meteorological and heatwave data.

### Data to request

- Maximum temperature

- Minimum temperature

- Relative humidity

- Rainfall

- Wind speed

- Solar radiation

- Heatwave observations

- Historical heatwave declarations

- Station-level observations

- AWS data, where available

- Historical climatological normals

## 2. Gujarat Health & Family Welfare Department / Commissionerate of Health & Family Welfare

Primary role: Health and hospital data.

Gujarat's government health information infrastructure includes the Gujarat Hospital Management Information System (GHMIS) under the Department of Health & Family Welfare. More recent Gujarat government documentation also identifies systems including HMIS, e-Mamta/TeCHO+, IHIP-IDSP, GERMIS, e-Hospital, ABDM and other health information systems within the state's health-data ecosystem.

### Data to request in aggregated/anonymised form:

- Heat-related illness

- Heatstroke/heat exhaustion

- Emergency admissions

- OPD/IPD indicators

- Cardiovascular conditions

- Respiratory conditions

- Renal/kidney-related indicators

- Mortality

- District-wise health indicators

- Hospital utilisation

- Seasonal/monthly disease indicators

- Relevant IDSP indicators

This should be explicitly requested as aggregated district/city-level data, consistent with the proposal's ethical commitment that no individual patient records or personally identifiable information will be collected.

Recommended agency: Commissionerate of Health & Family Welfare / Health & Family Welfare Department, Government of Gujarat

## 3. BISAG-N — Gandhinagar

Primary role: Geospatial, remote-sensing and spatial-data support.

This is particularly relevant because the project requires:

- Land Surface Temperature

- Vegetation

- Built-up density

- Land-use/land-cover

- Urban heat island analysis

- GIS-based vulnerability mapping

- Spatial databases

- District/city-level geospatial layers

BISAG-N's official mandate includes remote sensing, GIS, geoinformatics, photogrammetry, disaster management and decision-support systems. Its official site reports more than 550 projects, including more than 500 implemented projects, and describes its role in creating multi-purpose geospatial databases and providing spatial information for government planning and disaster management.  Its capabilities closely align with the proposal's GIS and remote-sensing requirements.

### Data/support to request

- Satellite-derived LST

- NDVI/vegetation layers

- Land-use/land-cover

- Built-up-area layers

- Urbanisation indicators

- GIS base layers

- Administrative boundaries

- Spatial infrastructure layers

- Disaster-risk layers

- Existing geospatial databases

- Historical satellite-derived datasets where available

Recommended agency: BISAG-N, Gandhinagar

# Recommended Three-Agency Data Architecture

| Agency | Data Domain | Key Variables | Use in Project |
| --- | --- | --- | --- |
| IMD – Meteorological Centre Ahmedabad | Climate & weather | Temperature, humidity, rainfall, wind, radiation, heatwaves | Heatwave forecasting |
| Gujarat Health & Family Welfare Department | Health | Hospital admissions, heat illness, mortality, disease indicators | Climate-health modelling |
| BISAG-N, Gandhinagar | GIS & remote sensing | LST, NDVI, land use, built-up area, spatial layers | HHRI & vulnerability mapping |

Proposed Data-Collection and Institutional Coordination Agencies:
The project will establish institutional coordination with relevant government and scientific agencies in Gujarat to ensure the availability, authenticity and continuity of historical datasets. The Meteorological Centre, Ahmedabad, India Meteorological Department (IMD), will be approached for historical meteorological and heatwave data. The Gujarat Health & Family Welfare Department/Commissionerate of Health & Family Welfare will be approached for aggregated and anonymised health indicators, hospital utilisation and disease surveillance information relevant to heat-health analysis. BISAG-N, Gandhinagar, will be approached for geospatial, remote-sensing and spatial database support, including land-surface temperature, vegetation, land-use/land-cover and urbanisation-related datasets. Data access will be subject to the respective agency's data-sharing policies, approvals and applicable confidentiality and data-governance requirements.

For primary data collection, we would separate the agencies collecting new field data from IMD, the Health Department and BISAG-N, which are primarily secondary/administrative data sources.

### Three agencies I would consider for primary data collection

| ### Agency | ### Location | ### Relevant capability | ### Potential role in your project |
| --- | --- | --- | --- |
| ### Prolific Research Pvt. Ltd. | ### Ahmedabad | ### Large-scale quantitative/qualitative fieldwork, healthcare research, survey programming, field data collection | ### Household, health-risk and vulnerable-population surveys |
| ### AIM Research | ### Ahmedabad | ### Social/health research, field surveys, GPS/photo verification, real-time validation | ### Household, worker and community vulnerability surveys |
| ### Shashwat Dalal & Associates | ### Ahmedabad | ### 350+ reported projects; social research, healthcare research, CAPI/CATI, F2F surveys | ### District-level community and outdoor-worker surveys |

### 1. Prolific Research Pvt. Ltd.

Prolific Research

This would be suitable for a relatively large and structured survey programme. The company states that it has operated from Ahmedabad since 2011 and provides quantitative and qualitative fieldwork, including healthcare research. Its current data-collection services include CAWI, CATI and mixed-mode fieldwork, with cleaned datasets available in SPSS, CSV and Excel formats.

For your project, ask them to collect:

- Household heat vulnerability survey

- Elderly-person vulnerability

- Outdoor-worker exposure

- Heat-related symptoms/experiences

- Access to drinking water and cooling facilities

- Housing characteristics

- Awareness of heatwave warnings

- Access to healthcare

- Heat Action Plan awareness

- Behavioural adaptation during heatwaves

### 2. AIM Research, Ahmedabad

AIM Research

AIM Research specifically describes capabilities in social research, field data collection and health-related research. It reports using GPS coordinates, photographs, audio verification, real-time validation, supervisor checks and offline data verification, together with mobile/CAPI-based tools.

That is particularly useful for your Heatwave Health Risk Index (HHRI) because you can attach geographical coordinates to selected observations.

For example:

Respondent → GPS location → vulnerability indicators → heat exposure → adaptive capacity

This would make the primary dataset more useful for subsequently integrating it with your GIS analysis.

### 3. Shashwat Dalal & Associates, Ahmedabad

Kaizen reports experience in primary research, social research, healthcare research, quantitative and qualitative studies, CAPI, CATI, and face-to-face surveys, and has completed more than 350 projects.

This makes it particularly relevant if you want field-based primary data rather than an online-only survey.

Potential assignment: Conduct district-level primary survey among vulnerable populations and heat-exposed workers using a structured CAPI questionnaire, with field supervisors responsible for sampling, respondent verification and quality control. I would particularly consider them for surveys involving:

- Construction workers

- Agricultural workers

- Street vendors

- Transport workers

- Sanitation workers

- Industrial/outdoor workers

- Low-income households

- Elderly populations

Before appointing any one agency, obtain technical and financial quotations from all three, and require the quotation to specify sample size, district coverage, sampling methodology, CAPI platform, enumerator training, GPS verification, back-check percentage, data cleaning and final dataset format.

Data architecture

Secondary/Institutional Data

IMD → Meteorological data
Gujarat Health Department → Health data
BISAG-N → GIS/remote-sensing data
Census/NFHS/SECC → Socio-demographic data

↓

Primary Data

Prolific Research / Kaizen / AIM Research → Household + outdoor-worker + vulnerable-population + healthcare/stakeholder surveys

↓

Integrated Data Repository

↓

AI/ML + GIS + HHRI

↓

Heatwave Health Risk Prediction + Dashboard + Alerts

This is much more defensible methodologically because the primary survey would fill the gaps in adaptive capacity, heat exposure behaviour and vulnerability that cannot be adequately obtained from historical secondary datasets alone. Your proposal specifically identifies these dimensions as central to the HHRI framework.

Justification for Human Resource Allocation – ₹21.60 lakh (50.70% of Total Project Cost)

The allocation of ₹21.60 lakh towards Human Resources, representing approximately 50.70% of the total project budget of ₹42.60 lakh, is justified by the highly knowledge-intensive and multidisciplinary nature of the proposed project. The project is not primarily an infrastructure procurement project; rather, its major outputs are based on scientific analysis, artificial intelligence and machine-learning model development, geospatial analysis, health-risk assessment, system development, validation and translation of research findings into an operational decision-support system.

The Research Associate – Climate Science & AI will process historical climate datasets, identify heatwave patterns, develop and validate AI/ML models (including Random Forest, XGBoost, and LSTM), conduct forecasting analysis, and document technical results. These activities constitute the core scientific component of the proposed Heatwave Early Warning and Health Risk Prediction System.

The Research Associate – GIS & Public Health will integrate health and vulnerability indicators, conduct GIS and spatial analysis, develop exposure-sensitivity-adaptive-capacity indicators, prepare heat-health vulnerability maps and contribute to the development of the Heatwave Health Risk Index (HHRI). These activities directly support the project's proposed district- and city-level vulnerability assessment.

The Data Analyst will undertake data cleaning, harmonisation, database development, quality assurance, integration of climate, health, socio-demographic and spatial datasets, and preparation of data pipelines required by the AI/ML and dashboard components.

The Project Coordinator will ensure continuous coordination among the research team, government departments, data-providing agencies and other stakeholders. The position will also support documentation, financial records, meetings, workshops, field activities and project reporting.

The project therefore requires sustained technical human resources throughout the 18-month implementation period. Personnel will be engaged directly in creating the project's principal deliverables rather than merely supporting administrative functions. These deliverables include the AI-based heatwave forecasting models, Heatwave Health Risk Index, GIS-based vulnerability maps, decision-support dashboard, mobile alert framework, validation outputs, technical reports and policy recommendations.

Furthermore, the project involves integrating multiple specialised domains—climate science, public health, artificial intelligence, machine learning, GIS, remote sensing, and data analytics. Such multidisciplinary integration cannot be achieved through one-time equipment procurement or outsourced services alone. Continuous engagement of appropriately skilled personnel is necessary for data interpretation, model development, validation, system integration, stakeholder interaction and knowledge transfer.

Accordingly, human resource allocation should be viewed as a direct project implementation cost, rather than administrative overhead. The proposed personnel constitute the technical workforce responsible for converting the project's data and computational resources into measurable scientific, technological and policy outputs.

| Human Resource | 18-month cost | Core implementation responsibility | Direct project outputs |
| --- | --- | --- | --- |
| Research Associate – Climate Science & AI | ₹7.20 L | Climate analysis, AI/ML, forecasting, validation | Heatwave forecasting models |
| Research Associate – GIS & Public Health | ₹6.30 L | GIS, health indicators, vulnerability analysis | HHRI & vulnerability maps |
| Data Analyst | ₹4.50 L | Data cleaning, integration, QA, pipelines | Integrated project database |
| Project Coordinator | ₹3.60 L | Field coordination, stakeholders, reporting | Workshops, coordination, documentation |
| Total | ₹21.60 L |  |  |

The remaining 49.30% (₹21.00 lakh) is actually directed toward implementation-related requirements such as:

- Data acquisition and processing — ₹2.50 lakh

- Cloud infrastructure and computing — ₹3.50 lakh

- GIS/analytical tools — ₹2.00 lakh

- Health data analysis/validation — ₹2.50 lakh

- Workshops/consultation/training — ₹1.50 lakh

- Dashboard/mobile alert development — ₹5.50 lakh

- Documentation/dissemination/publication — ₹1.50 lakh

- Institutional overhead — ₹2.00 lakh

These heads are already identified in the proposal's Budget Summary.

Thus, it would be misleading to describe the proposal as allocating "half the budget to salaries and only half to implementation." The human resources are themselves responsible for implementing the scientific and technological components.

Nature of Expenditure:
The proposed project is fundamentally an R&D and technology-development intervention, rather than an infrastructure-intensive project. Its principal deliverables are knowledge- and technology-based outputs, including AI/ML models, a Heatwave Health Risk Index, GIS vulnerability maps, a decision-support dashboard and a mobile alert framework. Consequently, expenditure on skilled human resources is intrinsically linked to project implementation. Unlike projects involving major physical infrastructure or equipment procurement, the value generated by this project is primarily derived from the expertise required to process heterogeneous datasets, develop analytical models, validate predictions, integrate geospatial and health information, develop software components and translate scientific results into an operational decision-support system.

This framing is consistent with the proposal's methodology, which integrates climate science, public health analytics, geospatial technologies and artificial intelligence.

# Another useful point: personnel cost is actually modest

The four positions together cost ₹21.60 lakh over 18 months, equivalent to an average of:

₹1.20 lakh per month for the entire project team

This is for four personnel, or an average budgeted cost of approximately:

₹30,000 per person per month

The proposal specifies:

- Climate Science & AI RA — ₹40,000/month

- GIS & Public Health RA — ₹35,000/month

- Data Analyst — ₹25,000/month

- Project Coordinator — ₹20,000/month.

Therefore, the 50.70% figure appears large when viewed as a percentage, but the actual personnel budget is relatively moderate for a multidisciplinary 18-month AI + climate + health + GIS project.

## "Why can't these activities be outsourced?"

You can respond:

Continuous technical personnel are necessary because the project involves iterative research and model development rather than one-time service procurement. Climate and health datasets will require repeated cleaning, integration, validation and interpretation. AI/ML models will require iterative training, testing, tuning and validation. Similarly, the HHRI and GIS vulnerability maps will require refinement based on stakeholder feedback and validation results. The dashboard and mobile alert components must subsequently be integrated with the analytical outputs. Maintaining dedicated project personnel ensures continuity of knowledge, reproducibility of analytical workflows, data governance, model documentation and long-term institutional ownership of the system.

This is particularly strong because your proposal explicitly includes model validation, cross-validation, sensitivity analysis, stakeholder review, dashboard user testing and stakeholder workshops.